# HR Analytics Dashboard Project Planner

### IBM HR Analytics Case Study

Project Owner: Surya
Project Type: End-to-End HR Analytics Dashboard
Dataset: IBM HR Employee Attrition Dataset
Tool Stack: Python, Excel, GitHub, Microsoft Word

# 1. Project Objective

Build an HR Analytics solution that identifies employee attrition drivers, uncovers high-risk employee segments, generates actionable business recommendations, and delivers insights through an interactive Excel dashboard.

# 2. Project Lifecycle

## Phase 1 — Business Understanding

### Activities

- Domain Research

- Stakeholder Analysis

- Problem Definition

- Business Objectives Definition

- Requirements Gathering

- KPI Identification

### Deliverables

- Domain Research Document

- Stakeholder Analysis

- BRD

- User Stories

- FRD

- KPI Dictionary

- Requirements Traceability Matrix

## Phase 2 — Data Understanding

### Activities

- Dataset Assessment

- Data Profiling

- Data Quality Review

- Data Cleaning

- Feature Engineering

- Data Validation

### Deliverables

- Data Assessment Report

- Data Profiling Report

- Data Cleaning Report

## Phase 3 — Exploratory Data Analysis

### Activities

- Attrition Overview Analysis

- Employee Demographic Analysis

- Department Analysis

- Job Role Analysis

- Satisfaction Analysis

- Compensation Analysis

- Correlation Analysis

### Deliverables

- EDA Notebook

- EDA Summary Report

## Phase 4 — Advanced Analytics

### Activities

- Attrition Driver Analysis

- Contribution Analysis

- Risk Matrix Development

- Priority Scoring

- Driver Selection

- 2-Dimensional Analysis

- 3-Dimensional Persona Analysis

### Deliverables

- Risk Matrix

- Driver Scan Report

- Contribution Analysis Report

- Priority Matrix

- Advanced Analytics Notebook

## Phase 5 — Insight Generation

### Activities

- Business Insight Identification

- Root Cause Investigation

- High-Risk Segment Analysis

- Recommendation Development

- Prescriptive Analytics

- Financial Impact Assessment

### Deliverables

- Insights Log

- Recommendation Log

- Business Question Resolution Log

- Prescriptive Action Framework

## Phase 6 — Dashboard Design & Development

### Activities

- KPI Selection

- Dashboard Wireframing

- Dashboard Development

- KPI Validation

- Dashboard Testing

### Deliverables

- Dashboard Wireframe

- Excel Dashboard

- KPI Validation Report

## Phase 7 — Quality Assurance

### Activities

- User Acceptance Testing (UAT)

- Dashboard Validation

- Data Validation

- KPI Validation

### Deliverables

- UAT Report

- Validation Results

## Phase 8 — Documentation

### Activities

- Executive Summary Creation

- Assumptions Documentation

- Limitation Documentation

- Lessons Learned Documentation

### Deliverables

- Executive Summary

- Data Limitation & Assumption Register

- Lessons Learned Document

## Phase 9 — Project Delivery

### Activities

- GitHub Repository Preparation

- Portfolio Case Study Preparation

- Final Presentation

- Project Closure

### Deliverables

- GitHub Repository

- Portfolio Case Study

- Final Dashboard

- Project Documentation Package

# 3. Success Criteria

The project will be considered successful if it:

- Identifies major attrition drivers.

- Highlights high-risk employee segments.

- Provides actionable business recommendations.

- Delivers a professional Excel dashboard.

- Supports HR decision-making through data-driven insights.

- Demonstrates end-to-end analytics capabilities suitable for a Data Analyst portfolio.

# 4. Final Project Outputs

### Analytics Assets

- Clean Dataset

- EDA Notebook

- Advanced Analytics Notebook

- Risk Matrix

- Priority Matrix

### Dashboard Assets

- Dashboard Wireframe

- Excel Dashboard

### Business Documents

- BRD

- FRD

- KPI Dictionary

- Insight Log

- Recommendation Log

- UAT Report

- Executive Summary

### Portfolio Assets

- GitHub Repository

- Portfolio Case Study

- Project Presentation

Project Status: Completed
Methodology: Analytics Lifecycle (Business Understanding → Data Understanding → Analytics → Visualization → Delivery)